## Experiments
Experiment ID | Phase | Block | Experiment | Hypothesis | Model | Dataset | Benchmark | Metrics | Statistical Test | Expected Outcome (pre-registered hypothesis, not a result) | Priority | Status | Owner | Planned Start (month) | Planned End (month) | Evidence Location | Notes
E00 | 2 | Data integrity | Point-in-time panel audit | Panel has no look-ahead: accounting data lagged by availability date; delisting returns applied. | n/a | CRSP/Compustat monthly 1963-2025 | CRSP value-weighted index; Ken French factors | Correlation of rebuilt FF factors with Ken French series; missing-share by year | Correlation > 0.95 threshold | Rebuilt factors match library closely | Must | Not started |  | 2 | 4
E01 | 3 | Signal library | Signal replication vs original papers | Rebuilt signals reproduce published long-short t-stats. | Univariate sorts | Signal panel (JKP/OpenAP definitions) | Chen-Zimmermann reproduced t-stats | Slope/R2 of our t-stats on theirs | Regression; share with t>1.96 | Slope near CZ2022's 0.88; R2 high | Must | Not started |  | 3 | 5
E02 | 3 | Signal library | Signal quality and decay profile | Signals differ in IC decay speed and turnover; fast signals are costlier. | Univariate IC by horizon 1-12m | Signal panel | n/a | Mean IC, ICIR, IC half-life, signal autocorrelation, implied turnover | Newey-West t on IC | Wide heterogeneity; price-based signals decay fastest | Must | Not started |  | 3 | 5
E03 | 3 | Signal library | Redundancy and clustering | Signals cluster into ~13 themes; within-theme redundancy is high. | Hierarchical clustering on rank correlations of signals and of signal returns | Signal panel | JKP 13 themes | Cluster purity, effective number of signals | Bootstrap cluster stability | Clusters broadly align with JKP themes | Should | Not started |  | 3 | 5
E10 | 4 | Baselines | Naive combinations | Equal-weight z-score, theme-EW, IC-weighted, ICIR-weighted and inverse-vol combinations are strong net-of-cost baselines. | Rule-based | Main universe | Each other | IC, gross/net Sharpe, turnover | Ledoit-Wolf Sharpe difference | Simple combos have low turnover and competitive net Sharpe | Must | Not started |  | 5 | 6
E11 | 4 | Baselines | Linear statistical combinations | Fama-MacBeth (Lewellen), ridge, elastic net, PLS improve IC over naive. | FM rolling slopes; ridge; ENet; PLS | Main universe | E10 best | OOS R2, IC, net Sharpe | Clark-West; DM | Modest IC gain; net gain uncertain | Must | Not started |  | 5 | 6
E12 | 4 | Baselines | Mean-variance signal-portfolio combination | KNS-style shrunk SDF over signal portfolios is a strong linear benchmark. | KNS2020 L2-shrinkage SDF | Signal long-short portfolios | E10/E11 | Net Sharpe | LW2008 test | Competitive gross, higher turnover | Must | Not started |  | 5 | 6
E13 | 4 | Baselines | Published ML benchmarks | GKX-style NN/GBDT and JKMP Portfolio-ML replicate approximately. | GKX NN3; LightGBM; JKMP Portfolio-ML code | Main universe | Published numbers | IC, OOS R2, net Sharpe | Tracking vs published | Directionally consistent replication | Must | Not started |  | 5 | 6
E14 | 4 | Baselines | Linear cost-aware PPP | DMNU-style linear PPP with costs is a strong implementable benchmark. | Linear PPP with TC | Main universe | E10-E13 | Net utility, net Sharpe | LW2008; SPA | Beats cost-agnostic linear models net | Must | Not started |  | 5 | 6
E20 | 5 | Factorial core | Cell LS-P: Linear, Static, Prediction loss | Reference cell. | Ridge | Main universe | - | All core metrics | - | Reference | Must | Not started |  | 6 | 9
E21 | 5 | Factorial core | Cell NS-P: Nonlinear, Static, Prediction loss | H1: nonlinearity raises gross IC/Sharpe vs LS-P. | LightGBM + NN ensemble | Main universe | E20 | Gross and net deltas | Clark-West; LW2008; SPA | Gross gain; net gain at least 50% smaller | Must | Not started |  | 6 | 9
E22 | 5 | Factorial core | Cell LC-P: Linear, Conditional, Prediction loss | H2a: conditioning adds little net value under prediction loss. | Ridge with signal x state interactions | Main universe | E20 | Net delta; turnover | SPA; Clark-West | Small/insignificant net gain | Must | Not started |  | 6 | 9
E23 | 5 | Factorial core | Cell NC-P: Nonlinear, Conditional, Prediction loss | Nonlinear conditioning under prediction loss increases turnover. | Gated MoE / GBDT with states | Main universe | E21, E22 | Net delta; turnover | SPA; MCS | Higher gross, uncertain net | Must | Not started |  | 6 | 9
E24 | 5 | Factorial core | Cell LS-E: Linear, Static, Economic loss | H3: economic loss improves net utility vs LS-P. | Linear PPP with TC | Main universe | E20 | Net utility | LW2008; SPA | Positive net gain | Must | Not started |  | 6 | 9
E25 | 5 | Factorial core | Cell NS-E: Nonlinear, Static, Economic loss | Nonlinear economic-loss learning (Portfolio-ML-type). | NN/RFF weight learner with TC | Main universe | E21, E24 | Net utility | SPA; MCS | Among best static cells | Must | Not started |  | 6 | 9
E26 | 5 | Factorial core | Cell LC-E: Linear, Conditional, Economic loss | H2b: conditioning adds net value when costs are internalised. | Conditional linear PPP with TC | Main universe | E24 | Net delta | SPA; Clark-West-type | Positive net gain (interaction) | Must | Not started |  | 6 | 9
E27 | 5 | Factorial core | Cell NC-E: Nonlinear, Conditional, Economic loss | Full model. | Gated nonlinear weight learner with TC | Main universe | All cells | Net utility; frontier | MCS; SPA; DSR; PBO | Best or statistically tied best | Must | Not started |  | 6 | 9
E28 | 5 | Factorial core | Uncertainty dimension (x8 cells) | H4: uncertainty shrinkage reduces turnover and raises net Sharpe. | Deep ensembles / bootstrap SE shrinkage | Main universe | Same cell without shrinkage | Turnover, net Sharpe | LW2008; paired bootstrap | Lower turnover; higher net Sharpe | Must | Not started |  | 6 | 9
E29 | 5 | Factorial core | ANOVA-style decomposition of net value | Main effects and interactions of the four factors can be separated. | Two-way/four-way decomposition on monthly net returns | Cell return panel | - | Main-effect and interaction contributions | Block bootstrap CIs | Objective main effect largest; state x objective interaction positive | Must | Not started |  | 6 | 9
E30 | 6 | Portfolio & costs | Implementable efficient frontier | Frontier ranking of cells is stable across AUM. | All cells | AUM $0.1bn/$1bn/$10bn (2020$) | 1/N; market | Net return vs risk curves | Bootstrap bands | Cost-aware cells dominate at high AUM | Must | Not started |  | 8 | 10
E31 | 6 | Portfolio & costs | Cost-model sensitivity | Conclusions robust to cost multipliers 0.5x-3x and alternative spread estimators. | Best cells | Main universe | - | Net Sharpe vs multiplier | Break-even multiplier | Ranking stable up to ~2x [hypothesis] | Must | Not started |  | 8 | 10
E32 | 6 | Portfolio & costs | Capacity | Break-even AUM differs by cell and state. | Best cells | AUM grid | - | Break-even AUM; net alpha decay | - | Cost-aware conditional cells have higher capacity | Should | Not started |  | 8 | 10
E33 | 6 | Portfolio & costs | Constraint variants | Long-only benchmark-relative and long-short results agree qualitatively. | Best cells | Main universe | - | Net IR; tracking error | LW2008 | Qualitatively similar | Should | Not started |  | 8 | 10
E34 | 6 | Portfolio & costs | Heuristic cost mitigation vs optimisation | Optimiser beats buy/hold banding net. | Banding (NMV2016) vs TC-optimiser | Main universe | NMV2016 banding | Net Sharpe | LW2008 | Optimiser better at high AUM | Should | Not started |  | 8 | 10
E40 | 8 | Inference | Data-snooping control over all cells | Best cell beats benchmark after accounting for all trials. | All configurations logged | Test period | JKMP Portfolio-ML; E14 | SPA p-values; StepM set; MCS | Hansen SPA; Romano-Wolf; MCS | Reported honestly whatever the outcome | Must | Not started |  | 11 | 13
E41 | 8 | Inference | Deflated Sharpe and PBO | Selected configuration's Sharpe survives deflation; PBO low. | All configurations | Validation/test | - | DSR; PBO (CSCV) | BLDP2014; BBLZ2017 | DSR > 0.95 target [hypothesis] | Must | Not started |  | 11 | 13
E42 | 8 | Inference | Factor-model alphas net of costs | Net alphas vs FF5+UMD, q5 and JKP themes. | Best cells | Test period | Factor models | Alpha, t-stat (NW) | Newey-West; GRS-type | Positive alpha vs FF5+UMD [hypothesis] | Must | Not started |  | 11 | 13
E43 | 8 | Inference | Multiverse / non-standard errors | Conclusions hold across reasonable design choices. | Design grid (window, universe, target, horizon) | Test period | - | Distribution of cell deltas | Share of specifications with same sign | Main-effect signs stable in >80% of specs [hypothesis] | Must | Not started |  | 11 | 13
E50 | 8 | Robustness | Subperiods | Results hold pre/post-2001 decimalisation, post-2008 and post-2020. | Best cells | Subsamples | - | Net Sharpe by period | Chow / Bai-Perron | Weaker after 2003 [hypothesis] | Must | Not started |  | 11 | 13
E51 | 8 | Robustness | Universe variants | Results hold ex-microcaps, NYSE-top-500, all stocks. | Best cells | Universes | - | Net metrics | LW2008 | Gains smaller in large caps | Must | Not started |  | 11 | 13
E52 | 8 | Robustness | Horizon and rebalancing | Monthly vs quarterly rebalancing and 1/3/6/12m targets. | Best cells | Main universe | - | Net Sharpe; turnover | - | Longer horizons help net | Should | Not started |  | 11 | 13
E53 | 8 | Robustness | Placebo states | Randomised or shuffled state variables remove conditioning gains. | Conditional cells | Main universe | Real states | Net delta | Permutation test | Placebo gains ~0 | Must | Not started |  | 11 | 13
E54 | 8 | Robustness | Pre-publication signal gating | Using only signals published before t does not overturn conclusions. | All cells | Gated library | Full library | Net deltas | - | Smaller levels, same ranking [hypothesis] | Must | Not started |  | 11 | 13
E55 | 8 | Robustness | International out-of-sample | Ranking of cells holds in developed ex-US markets. | Best cells | JKP developed markets | - | Net Sharpe by region | - | Direction holds with weaker magnitude [hypothesis] | Could | Not started |  | 11 | 13
E56 | 8 | Robustness | Seeds and hyperparameter perturbation | NN results stable across 10+ seeds and +/-1 grid step. | NN cells | Main universe | - | Dispersion of net Sharpe | - | Low dispersion relative to cell gaps | Must | Not started |  | 11 | 13
E60 | 7 | Interpretation | Economic feature importance by theme | Net value concentrated in slow themes (value, profitability, investment) and liquidity-aware use of fast themes. | Leave-theme-out net utility; SHAP | Main universe | - | Delta net utility by theme | Bootstrap CIs | Value/quality high; short-term reversal low net | Must | Not started |  | 9 | 11
E61 | 7 | Interpretation | State-dependent signal weights | Momentum weight falls in high-volatility post-crash states; short-leg anomaly weight rises with sentiment. | Implied weights from conditional cells | Main universe | DM2016; SYY2012 predictions | Implied weight paths | Regression of weights on states | Consistent with DM2016/SYY2012 [hypothesis] | Must | Not started |  | 9 | 11
E62 | 7 | Interpretation | Limits-to-arbitrage mechanism | Gross ML gains concentrate in high-IVOL/illiquid stocks; cost-aware learning shifts exposure away. | Portfolio characteristic tilts | Main universe | ACM2023 findings | Exposure to IVOL, illiquidity, size | Difference tests | Consistent with ACM2023 [hypothesis] | Must | Not started |  | 9 | 11
E63 | 7 | Interpretation | Trading-speed test of CDS2020 | Optimal trading speed rises in liquid, persistent states. | Conditional economic-loss cells | Main universe | CDS2020 theory | Turnover by liquidity state | Regression | Positive relation [hypothesis] | Should | Not started |  | 9 | 11
E64 | 7 | Interpretation | Alpha-risk alignment diagnostics | Nonlinear alphas show larger ex-post risk underestimation. | All cells | Main universe | CSS2012 | Bias statistic | - | Larger bias for nonlinear cells | Could | Not started |  | 9 | 11

## Summary
Experiment progress (live formulas)
Change Status in the Experiments sheet; this sheet updates automatically
Block | Not started | In progress | Blocked | Done | Dropped | Total | % Done
Data integrity
Signal library
Baselines
Factorial core
Portfolio & costs
Inference
Robustness
Interpretation
All experiments
Priority | Count | Done
Must
Should
Could

## Factorial_Cells
16-cell factorial design with orthogonal contrast coding (formulas)
Contrast columns (+1/-1) and interactions are formulas; use them to regress monthly net returns of cells on effects (E29)
Cell | Form | Conditioning | Objective | Uncertainty | Experiment | x_Nonlinear | x_State | x_Economic | x_Uncertainty | State x Economic | Nonlinear x Economic | Nonlinear x State | Uncertainty x Economic
L-S-P-0 | Linear | Static | Prediction | None | E20
L-S-P-U | Linear | Static | Prediction | Ensemble shrinkage | E20 + E28
L-S-E-0 | Linear | Static | Economic | None | E24
L-S-E-U | Linear | Static | Economic | Ensemble shrinkage | E24 + E28
L-C-P-0 | Linear | State | Prediction | None | E22
L-C-P-U | Linear | State | Prediction | Ensemble shrinkage | E22 + E28
L-C-E-0 | Linear | State | Economic | None | E26
L-C-E-U | Linear | State | Economic | Ensemble shrinkage | E26 + E28
N-S-P-0 | Nonlinear | Static | Prediction | None | E21
N-S-P-U | Nonlinear | Static | Prediction | Ensemble shrinkage | E21 + E28
N-S-E-0 | Nonlinear | Static | Economic | None | E25
N-S-E-U | Nonlinear | Static | Economic | Ensemble shrinkage | E25 + E28
N-C-P-0 | Nonlinear | State | Prediction | None | E23
N-C-P-U | Nonlinear | State | Prediction | Ensemble shrinkage | E23 + E28
N-C-E-0 | Nonlinear | State | Economic | None | E27
N-C-E-U | Nonlinear | State | Economic | Ensemble shrinkage | E27 + E28
Check: every contrast column sums to zero (orthogonal design)

## Roadmap_Gantt
Roadmap Gantt (formula-driven)
Edit Start/End months; cells with 1 are shaded by conditional formatting
Phase | Start month | End month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1. Literature + research design | 1 | 2
2. Data infrastructure | 2 | 4
3. Alpha signal library | 3 | 5
4. Baseline models | 5 | 6
5. ML signal combination | 6 | 9
6. Portfolio construction | 8 | 10
7. Robust backtesting | 9 | 11
8. Robustness + statistical testing | 11 | 13
9. Paper writing | 12 | 15
10. Journal submission | 15 | 16

## Reviewer_Checklist
Reviewer-proof checklist tracker
Status dropdown; completion % recalculates |  |  | Completion:
Section | Checklist item | Status | Evidence location | Owner
A. Contribution and positioning | The research question is stated in one sentence as an economic question, not a model description. | Not started
A. Contribution and positioning | The contribution statement names the closest papers (JKMP2026, SWZ2023, DMNU2020, DMU2024, GKX2020, ACM2023, CHK2024, LMNS2025) and says what is new relative to each. | Not started
A. Contribution and positioning | The closest-prior-art tracker has been re-run within 2 weeks of submission (SSRN, NBER, arXiv, conference programmes, forward citations). | Not started
A. Contribution and positioning | No "first to" claim appears unless the tracker supports it. | Not started
A. Contribution and positioning | The hypotheses were pre-registered (dated document or OSF/AEA registry) before the lockbox was opened. | Not started
A. Contribution and positioning | Null or negative results are reported, with power discussion. | Not started
B. Data and point-in-time integrity | All data sources, pull dates and versions are documented. | Not started
B. Data and point-in-time integrity | Accounting variables are lagged by availability (≥ 4 months annual; RDQ quarterly) and unit tests prove it. | Not started
B. Data and point-in-time integrity | Universe formed at t from all live securities (no survivorship). | Not started
B. Data and point-in-time integrity | CRSP delisting returns are applied; the convention for missing values is documented. | Not started
B. Data and point-in-time integrity | Corporate actions are handled via CRSP adjustment factors and total returns. | Not started
B. Data and point-in-time integrity | Microcaps are excluded from the main universe; results including them are in robustness. | Not started
B. Data and point-in-time integrity | Macro/state variables use real-time (vintage) data or market-based measures; no smoothed regime probabilities. | Not started
B. Data and point-in-time integrity | Rebuilt standard factors correlate > 0.95 with the Ken French library. | Not started
B. Data and point-in-time integrity | Signal replication statistics versus Chen-Zimmermann/JKP are reported. | Not started
B. Data and point-in-time integrity | Missing-data handling is described, with robustness to imputation methods . | Not started
C. Validation and leakage | Walk-forward splits, refit schedule, embargo and purging are documented in a split calendar. | Not started
C. Validation and leakage | No hyperparameter is tuned on test data; the validation windows strictly precede test years. | Not started
C. Validation and leakage | Lockbox period (2021-2025) opened once, after the specification freeze; the freeze date is recorded. | Not started
C. Validation and leakage | Every configuration tried is logged (count reported in the paper). | Not started
C. Validation and leakage | Label overlap for multi-month horizons is purged. | Not started
C. Validation and leakage | NN results report dispersion across ≥ 10 seeds. | Not started
D. Benchmarks | Naive composites (EW, theme-EW, IC-weighted, ICIR-weighted, inverse-vol) are included. | Not started
D. Benchmarks | Linear baselines (Lewellen FM, ridge, ENet, PLS) are included. | Not started
D. Benchmarks | Strongest published implementable benchmarks are included (JKMP Portfolio-ML from authors' code; DMNU linear PPP). | Not started
D. Benchmarks | Benchmarks receive the same tuning budget and cost model as proposed cells. | Not started
D. Benchmarks | 1/N and market portfolios are reported . | Not started
D. Benchmarks | Heuristic cost mitigation (banding) is compared . | Not started
E. Portfolio construction, costs and capacity | Net-of-cost results are primary; gross results are secondary. | Not started
E. Portfolio construction, costs and capacity | Cost model components (spread, impact, commission, borrow) and calibration sources are stated. | Not started
E. Portfolio construction, costs and capacity | Sensitivity to cost multipliers (0.5×-3×) and alternative spread estimators is shown. | Not started
E. Portfolio construction, costs and capacity | AUM grid and break-even AUM (capacity) are reported. | Not started
E. Portfolio construction, costs and capacity | Turnover, holding period and cost drag are reported for every strategy. | Not started
E. Portfolio construction, costs and capacity | Constraint set (neutralities, position/trade/participation limits) is identical across cells. | Not started
E. Portfolio construction, costs and capacity | Execution lag (≥ 1 trading day) is enforced. | Not started
E. Portfolio construction, costs and capacity | Short-leg contribution and borrow-cost treatment are disclosed. | Not started
E. Portfolio construction, costs and capacity | Long-only variant reported. | Not started
F. Statistical inference | HAC (Newey-West) t-stats for means and alphas. | Not started
F. Statistical inference | Sharpe-ratio differences tested with Ledoit-Wolf (2008) bootstrap. | Not started
F. Statistical inference | Nested forecast comparisons with Clark-West; others with Diebold-Mariano. | Not started
F. Statistical inference | SPA and Reality Check versus the strongest benchmark; StepM for which cells win; MCS reported. | Not started
F. Statistical inference | Deflated Sharpe ratio uses the logged trial count; PBO via CSCV reported. | Not started
F. Statistical inference | Factorial effects and Shapley attributions have bootstrap confidence intervals. | Not started
F. Statistical inference | Alphas versus FF5+UMD, q5 and JKP themes (net of costs). | Not started
F. Statistical inference | Multiple theme/signal claims are FDR-controlled. | Not started
F. Statistical inference | Non-standard errors across the pre-declared multiverse are reported. | Not started
G. Robustness | Subperiods, including pre/post decimalisation and post-2008. | Not started
G. Robustness | Universes: all stocks, ex-micro, top-500. | Not started
G. Robustness | Horizons and rebalancing frequency. | Not started
G. Robustness | Risk-model alternatives. | Not started
G. Robustness | Rolling vs expanding windows. | Not started
G. Robustness | Placebo (shuffled) states. | Not started
G. Robustness | Publication-gated signal library. | Not started
G. Robustness | International (developed ex-US) evidence or a stated reason for exclusion. | Not started
G. Robustness | Hyperparameter perturbations. | Not started
H. Economic interpretation | Economic feature importance (net utility loss from dropping themes). | Not started
H. Economic interpretation | SHAP/ALE interpretation for prediction cells, with correlated-feature caveats. | Not started
H. Economic interpretation | Implied state-dependent weights are linked to DM2016, SYY2012 and CDS2020 predictions. | Not started
H. Economic interpretation | Limits-to-arbitrage tilts (IVOL, illiquidity, size, distress) by cell. | Not started
H. Economic interpretation | A clear answer to "why does it work (or fail)?" appears in the introduction. | Not started
I. Reproducibility and presentation | Replication package: code, environment file, README, pseudo-data for licensed inputs (JF/RFS/MS policies). | Not started
I. Reproducibility and presentation | Figures readable in grayscale; tables have units and sample periods. | Not started
I. Reproducibility and presentation | The abstract states net-of-cost results and the holdout period. | Not started
I. Reproducibility and presentation | Internet appendix contains all robustness tables referenced. | Not started
I. Reproducibility and presentation | Limitations section covers cost-model uncertainty, US focus, and data licences. | Not started